## Task Tracker
Brookline Budget Reform — Project Task Tracker
Update status directly in this sheet. Filter by Branch, Status, or Priority to focus your work session.
Branch | Workstream | Task | Status | Priority | Owner | Due / Notes | Dependency | Output | Last Updated
B1 · Econ Dev | Site inventory | Pull Brookline commercial parcel data from Assessor's Office | To Do | High |  | brooklinema.gov/assessor | — | Commercial parcel spreadsheet | —
B1 · Econ Dev | Site inventory | Apply RKG Fiscal Impact Model to top 10 development sites | To Do | High |  | Need RKG model access from Planning Dept | Parcel data first | Revenue per site estimates | —
B1 · Econ Dev | Site inventory | Build prioritized 10-year development pipeline with timeline estimates | To Do | Medium |  |  | Site estimates | Pipeline doc | —
B1 · Econ Dev | Zoning reform | Map current FAR and height limits for top commercial corridors (Beacon St, Harvard St, Rt 9) | To Do | High |  | Zoning By-Law + GIS maps | — | Zoning gap analysis | —
B1 · Econ Dev | Zoning reform | Research Cambridge/Somerville as-of-right zoning models and revenue outcomes | To Do | Medium |  | Web research + DLS snapshots | — | Comparable zoning memo | —
B1 · Econ Dev | Zoning reform | Draft specific zoning changes needed to unlock top 5 stalled sites | To Do | Medium |  |  | Zoning gap analysis | Zoning reform proposal | —
B1 · Econ Dev | PILOT program | Obtain full list of tax-exempt properties from Assessor | To Do | High |  | brooklinema.gov/assessor | — | Non-profit property list | —
B1 · Econ Dev | PILOT program | Estimate value of non-exempt use properties for top 20 non-profit holders | To Do | Medium |  |  | Non-profit property list | PILOT revenue estimate | —
B1 · Econ Dev | PILOT program | Research existing Brookline PILOT agreements (e.g. 2 Brookline Place, Newbury on Fisher Hill) | To Do | Medium |  | Town Counsel / Assessor records | — | PILOT precedent memo | —
B1 · Econ Dev | PILOT program | Design structured PILOT program with incentives and consequences | To Do | Low |  |  | Revenue estimate + precedents | Draft PILOT policy | —
B1 · Econ Dev | Asset monetization | Audit municipal parking lots: capacity, current revenue, lease potential | To Do | Medium |  | DPW + Parking Dept data | — | Parking revenue analysis | —
B1 · Econ Dev | Asset monetization | Research golf course revenue vs. comparable municipal courses | To Do | Low |  | Recreation Dept financials | — | Golf course memo | —
B1 · Econ Dev | Asset monetization | Map school building off-hours capacity and current rental rates vs. market | To Do | Medium |  | PSB facilities data + E&RSC appendix | — | Facilities rental gap analysis | —
B1 · Econ Dev | OOD SpEd expansion | Quantify current OOD SpEd program capacity and waitlist demand | To Do | High |  | PSB FY27 budget + DESE tuition tables | — | OOD capacity memo | —
B1 · Econ Dev | OOD SpEd expansion | Model revenue from expanding Winthrop House, ALC, LAHB to external students | To Do | High |  | PSB FY27 budget (published Feb 5, 2026) | Capacity memo | OOD revenue model | —
B1 · Econ Dev | Governance | Draft proposed org structure: SB econ dev lead + elevated planning division | To Do | Medium |  | E&RSC recommendations as baseline | — | Governance proposal | —
B2 · Legislative | METCO SpEd costs | Pull DESE SY24 in-district SpEd per-pupil cost data for Brookline | To Do | High |  | dese.mass.edu — public data | — | SpEd cost baseline | —
B2 · Legislative | METCO SpEd costs | Quantify non-resident SpEd enrollment breakdown (METCO vs Materials Fee) | To Do | High |  | PSB enrollment data — partial in E&RSC appendix | — | Non-resident SpEd enrollment table | —
B2 · Legislative | METCO SpEd costs | Calculate total annual unreimbursed SpEd cost with confidence interval | To Do | High |  |  | Cost baseline + enrollment table | Core financial claim ($4M figure) | —
B2 · Legislative | Coalition mapping | Research METCO enrollment at Newton, Wellesley, Lexington + their SpEd burden | To Do | High |  | DESE public data + district annual reports | — | Coalition data brief | —
B2 · Legislative | Coalition mapping | Identify CFO/Superintendent contacts at Newton, Wellesley, Lexington for outreach | To Do | Medium |  | District websites | Coalition data | Contact list | —
B2 · Legislative | Coalition mapping | Estimate total statewide unreimbursed METCO SpEd cost across all receiving districts | To Do | Medium |  | DESE METCO program data | Coalition data | Statewide impact figure | —
B2 · Legislative | Legislative strategy | Identify Brookline's current State House delegation (Rep + Senator) | To Do | High |  | malegislature.gov | — | Delegation contact sheet | —
B2 · Legislative | Legislative strategy | Search for existing bills on METCO reimbursement, Prop 2½, Ch. 70 reform | To Do | High |  | malegislature.gov + MMA legislative tracker | — | Existing bills memo | —
B2 · Legislative | Legislative strategy | Determine best legislative vehicle: Ed Reform amendment vs. budget line item vs. Home Rule | To Do | Medium |  | Town Counsel consultation recommended | Existing bills memo | Legislative pathway recommendation | —
B2 · Legislative | Chapter 70 reform | Analyze Brookline's Chapter 70 aid vs. foundation budget — is Brookline underfunded? | To Do | Medium |  | DESE Foundation Budget data (public) | — | Ch. 70 gap analysis | —
B2 · Legislative | Chapter 70 reform | Research MMA's Chapter 70 reform proposals and Brookline's historical position | To Do | Low |  | mma.org research + MMA 'Weathering the Storm' report | — | Ch. 70 reform memo | —
B2 · Legislative | New revenue tools | Research MA transfer tax legislation status (Boston/Cambridge precedent) | To Do | Medium |  | malegislature.gov + Boston City Council records | — | Transfer tax memo | —
B2 · Legislative | New revenue tools | Inventory Home Rule petition options available to Brookline for new revenue tools | To Do | Low |  | MA GL Home Rule authority + Town Counsel | — | Home Rule options list | —
B3 · OPEB Pivot | OPEB liability | Extract key figures from GASB 74/75 actuarial report (in E&RSC appendix) | To Do | High |  | Already in E&RSC appendix — June 30, 2024 data | — | OPEB liability baseline | —
B3 · OPEB Pivot | OPEB liability | Determine current annual required contribution (ARC) and unfunded liability total | To Do | High |  | GASB 74/75 report + MA PERAC data | Liability baseline | OPEB funding requirement | —
B3 · OPEB Pivot | OPEB liability | Project OPEB liability growth at current trajectory through FY35 | To Do | Medium |  | Actuarial growth rate assumptions | Funding requirement | OPEB projection model | —
B3 · OPEB Pivot | $40M scenarios | Build Scenario A model: all $40M to OPEB starting FY31 | To Do | High |  | E&RSC Long-Range Financial Plan as baseline | OPEB projection | Scenario A model | —
B3 · OPEB Pivot | $40M scenarios | Build Scenario B model: $25M OPEB / $15M structural relief split | To Do | High |  |  | Scenario A model | Scenario B model | —
B3 · OPEB Pivot | $40M scenarios | Build Scenario C model: dynamic allocation tied to deficit + econ dev revenue | To Do | Medium |  |  | Scenarios A+B | Scenario C model | —
B3 · OPEB Pivot | $40M scenarios | Build Scenario D model: healthcare reform first, then OPEB pivot from stronger position | To Do | Medium |  |  | Healthcare analysis | Scenario D model | —
B3 · OPEB Pivot | Moody's sensitivity | Map which Moody's scoring factors OPEB funding affects (from E&RSC appendix scorecard) | To Do | High |  | Moody's scorecard already in E&RSC appendix | — | Moody's factor map | —
B3 · OPEB Pivot | Moody's sensitivity | Model rating impact under Scenarios A-D — identify downgrade threshold | To Do | High |  | Requires financial advisor input ideally | Moody's factor map + scenarios | Rating sensitivity analysis | —
B3 · OPEB Pivot | Healthcare reform | Pull MA Group Insurance Commission (GIC) current rate schedules | To Do | High |  | mass.gov/gic — public | — | GIC rate comparison | —
B3 · OPEB Pivot | Healthcare reform | Model annual savings from reducing employer premium share: 83% → 76% → GIC | To Do | High |  | E&RSC comparable community data + GIC rates | GIC rates | Healthcare savings model | —
B3 · OPEB Pivot | Healthcare reform | Research collective bargaining constraints on changing premium contribution rate | To Do | Medium |  | Brookline union contracts + MA GL c.32B | — | CBA constraints memo | —
B3 · OPEB Pivot | Comparables | Research how Newton, Wellesley, Lexington have planned for pension-to-OPEB transition | To Do | Medium |  | Comparable city annual reports + MA PERAC | — | Comparable OPEB strategies | —
B3 · OPEB Pivot | Deficit projection | Project operating deficit FY27–FY35 under 3 scenarios (no reform / B1+B2 conservative / optimistic) | To Do | Low |  | E&RSC Long-Range Plan + branch research outputs | All branch research | Integrated deficit model | —
Synthesis | Proposal draft | Draft Branch 1 section with data-backed recommendations and impact estimates | To Do | Medium |  |  | All B1 research complete | Branch 1 draft | —
Synthesis | Proposal draft | Draft Branch 2 section with legislative pathway and coalition strategy | To Do | Medium |  |  | All B2 research complete | Branch 2 draft | —
Synthesis | Proposal draft | Draft Branch 3 section with scenario analysis and policy recommendation | To Do | Medium |  |  | All B3 research complete | Branch 3 draft | —
Synthesis | Proposal draft | Write integrated proposal narrative connecting all three branches | To Do | Low |  |  | All branch drafts | Full proposal draft | —
Synthesis | Proposal draft | Build combined impact model showing phased deficit reduction FY27–FY35 | To Do | Low |  |  | All branch models | Master financial model | —
Synthesis | Delivery | Identify target audience and presentation format (Select Board / Town Meeting / public) | To Do | Low |  |  | Full draft | Delivery strategy | —
Synthesis | Delivery | Prepare executive summary (1-2 pages) for non-technical audience | To Do | Low |  |  | Full draft | Executive summary | —

## Dashboard
Project Dashboard
Formulas pull live from Task Tracker sheet. Update statuses there and this refreshes automatically.
Overall Progress
Branch | Total Tasks | Done | In Progress | Blocked | To Do | % Complete
Branch 1 — Economic Development | 16 | 0 | 0 | 0 | 16 | 0%
Branch 2 — Legislative Strategy | 13 | 0 | 0 | 0 | 13 | 0%
Branch 3 — OPEB Pivot | 14 | 0 | 0 | 0 | 14 | 0%
Synthesis & Delivery | 7 | 0 | 0 | 0 | 7 | 0%
TOTAL | 50 | 0 | 0 | 0 | 50 | 0%
Priority Breakdown — All Open Tasks
Priority | Total | Done | Remaining
High | 20 | 0 | 20
Medium | 21 | 0 | 21
Low | 9 | 0 | 9

## How To Use
How To Use This Tracker
UPDATING TASKS
Status options: | To Do ¦ In Progress ¦ Done ¦ Blocked
Priority options: | High ¦ Medium ¦ Low
Owner: | Enter your name or initials in the Owner column
Last Updated: | Type today's date when you change a row
Due / Notes: | Use this for deadlines, context, or where to find source data
FILTERING
Filter by Branch: | Click the dropdown on column A to focus on B1, B2, B3, or Synthesis
Filter by Status: | Column D — show only 'To Do' or 'In Progress' to see what's active
Filter by Priority: | Column E — start each session by showing only 'High' priority tasks
Clear filters: | Data > Clear Filter, or click the filter icon and select All
STATUS COLORS
To Do | Gray — not started yet
In Progress | Yellow — actively being worked on
Done | Green — complete
Blocked | Red — waiting on something external
DASHBOARD
Live counts: | The Dashboard sheet pulls live COUNTIF formulas from Task Tracker
Refresh: | Dashboard updates automatically as you change statuses — no action needed
ADDING NEW TASKS
Add rows: | Insert a new row anywhere in the Task Tracker and fill in all columns
Branch values: | Must match exactly: B1 · Econ Dev ¦ B2 · Legislative ¦ B3 · OPEB Pivot ¦ Synthesis
Status values: | Must match exactly: To Do ¦ In Progress ¦ Done ¦ Blocked
Priority values: | Must match exactly: High ¦ Medium ¦ Low
WORKFLOW SUGGESTION
Start of session: | Filter Status = In Progress. See what you were working on.
Research sprint: | Filter Priority = High, Status = To Do. Pick your next task.
End of session: | Update statuses. Add notes in Due/Notes. Update Last Updated date.